## 01_Roadmap_OKRs
Year | Quarter | Strategic Objective (OKR) | Primary KPI | Secondary KPI | Core Themes | Platforms | Owner | Budget (GBP) | Key Milestones | Start Date | End Date | Status
2025 | Q3 | Build LinkedIn thought-leadership & generate qualified leads | 30 SQLs | +1,500 followers | Trends / Case studies / Founder POV | LinkedIn (Company + Adam) | Marketing Lead | 15000 | Publish 1 flagship report; 2 client success stories; launch newsletter | 2025-07-01 | 2025-09-30 | Planning
2025 | Q3 | Test RED/XHS content playbook & creator collaboration | 3 creator collabs | 5 qualified inbound leads | Platform explainers / Localisation tips | Xiaohongshu (Company) | China Ops Lead | 8000 | Open XHS account; Post 8x; run 1 micro KOL test | 2025-07-15 | 2025-09-30 | Planning
2025 | Q4 | Scale high-performing formats & start paid boosting to ICP | 40 SQLs | +2,500 followers | Case studies / Data dashboards | LinkedIn + XHS | Growth Manager | 25000 | 2 webinars; 1 live Q&A; paid boost on 4 best posts | 2025-10-01 | 2025-12-31 | TBD

## 02_Events_Campaigns
Year | Quarter | Month | Event Name | Type | Platform | Target Audience Tier | YASO Participation Type | Related Content / Campaign | Pre-event Activation Plan | During-event Plan | Post-event Follow-up | Key Partners / KOLs | Owner | Budget (GBP) | Start Date | End Date | Status | Notes
2025 | Q4 | November | Double 11 / 双十一 | E-commerce Campaign | Douyin + RED | High | KOL campaign + product launch support | Preheat campaign + Live selling week | KOL teaser content + Trend posts on RED | Real-time RED/Douyin livestream collaboration | Case study recap + performance dashboard | Top CN KOLs | China Ops Lead | 10000 | 2025-10-15 | 2025-11-11 | Planned
2025 | Q4 | August | Cosmoprof Asia (HK) | Industry Expo | LinkedIn + RED | Medium-High | Exhibitor + Founder networking | Pre-event warm-up + trend posts on LinkedIn | Booth livestream + founder interview content | LinkedIn + XHS post-event recap | Newsletter + booth video cut | APAC distributors | Marketing Lead | 12000 | 2025-11-10 | 2025-11-14 | Planned
2025 | Q4 | August | China Beauty Expo (Shanghai) | Trade Show | RED | High | Exhibitor + B2B Matching | RED entry playbook soft launch | Pre-event creator collabs (RED 3-posts series) | Event-day highlight feed | KOL reactions + carousel summary | Mid-tier RED creators | China Ops Lead | 9000 | 2025-05-20 | 2025-05-22 | Completed

## 03 Clients Prioritize
Type | Criteria | Case study | Strategic Focus
High-Priority Leads | Medium, Medium-High, or High exposure to China, but not yet active in social commerce (e.g., Douyin/RED) | Elemis、Aurelia London、Noble Panacea | Primary targets; share case studies and educational content to initiate engagement
Secondary Leads | Low or Low-Medium exposure, or present in China but not active on Douyin/RED | OSKIA、Wildsmith Skin、Heathcote & Ivory、Delilah Cosmetics | Potential candidates; attract attention with trend-focused content
Irrelevant Leads | Already fully entered the Chinese market (e.g., large players like Mac Cosmetics) or not aligned with social commerce strategy | The Ordinary | Exclude or deprioritize in content and outreach

## 04_Content_Calendar
Year | Quarter | Month | Week | Platform | Account | Audience Tier | Content Theme | Post Title | Format | CTA（Call To Action） | Primary KPI | Secondary KPI | Frequency | Multi-Channel Plan | Paid Ads (Y/N) | Owner | Status | Notes/Links
2025 | Q3 | July | W4 | LinkedIn | YASO Company | High | Client Success Stories | UK skincare brand hit Douyin Top 10 in 60 days | Carousel + short post | Book a 30-min diagnostic | SQLs (Leads) | Engagement rate |  | Turn into XHS long-form note | Y | Content Lead | Drafting
2025 | Q3 | August | W1 | LinkedIn | Adam Knight (Founder) | High | Founder & Team Stories | Why founders should keep control when entering China | Video (90s) + long text | DM me for the checklist | DMs / Inbound | Views |  | Clip into shorts for XHS & add Chinese caption | N | Founder | Planned
2025 | Q3 | August | W2 | Xiaohongshu | YASO Company | Medium | Go-to-Market Tips | 入华5大常见错误：价格、渠道、直播权重... | 长图文笔记 + 模板下载 | 评论领取入华检查清单 | 评论+收藏 | 跳转私信 |  | Summarise to LinkedIn doc post | N | China Ops | Planned
2025 | Q3 | August | W3 | LinkedIn | YASO Company | Medium | Platform Trend Insights | Douyin vs RED 2025: where premium beauty scales faster | Infographic + doc post | Download the mini-report | Downloads | Shares |  | Reuse charts on XHS with CN captions | Y | Data Analyst | Idea
2025 | Q3 | September | W1 | LinkedIn | Adam Knight (Founder) | Low | Platform Trend Insights | Lessons from 618: why Tmall logic fails on Douyin | Long post + chart | Join our LinkedIn Live (date) | Live sign-ups | Comments |  | Turn highlights into newsletter | N | Founder | TBD
2025 | Q3 | September | W2 | Xiaohongshu | YASO Company | High | Client Success Stories | 英澳独立品牌在RED的冷启动策略案例 | 短视频+拆解图 | 评论区领取冷启动SOP | Leads (DM) | 收藏/转发 |  | Cut into LinkedIn carousel (EN) | Y | China Ops | TBD

## 05_Audience_Theme_Map
Audience Tier | Pain Points | Messaging Angle | Priority Themes (1-4) | Preferred Formats | Primary CTA | Nurture Path / Asset
High | Need fast, transparent, ROI-positive China social commerce entry | show them the potentials of different social media platform, like Douyin | 1) Client Success Stories 2) Founder Stories 3) Trend Insights 4) Go-to-Market Tips | Case study carousels, dashboards, 90s founder videos | Book a diagnostic / DM founder | Casebook + Data dashboard demo
Medium | Curious about China but unsure of platform & budget fit | Practical GTM frameworks, mistakes to avoid, lightweight tests | 1) Go-to-Market Tips 2) Trend Insights 3) Founder Stories 4) Client Success Stories | How-to posts, infographics, doc posts, XHS long notes | Download checklist / Comment to get template
Low | Already in China or no social commerce focus | High-level insights & benchmarks to keep awareness | 1) Trend Insights 2) Founder POV 3) Go-to-Market Tips 4) Client Stories | Long-form thought leadership, webinars | Subscribe to newsletter | Quarterly trend newsletter

## 06 Original Content Theme
Content Theme | Objective | Sample Post Title | Successful Example 1 | Successful Example 2 | Successful Example 3 | Successful Example 4
Client Success Stories | Convince high-intent brands （High） | “How YASO helped a UK brand grow on Douyin in just 90 days” | https://www.linkedin.com/posts/saahil-nayar-14b231a8_glossgirl-amazonbestsellers-activity-7351654967188865025-r3_Q?utm_source=share&utm_medium=member_desktop&rcm=ACoAAEcGAMgByNL8VRlNW9no7uklF_wVTugH2WU
Go-to-Market Tips | Educate brands with low awareness of China （Secondary） | “What’s working (and not) for premium skincare brands on RED” | https://www.linkedin.com/posts/tyarna-agyekum_most-aesthetic-feeds-beauty-brands-activity-7351174899618488320-M7Qe?utm_source=share&utm_medium=member_desktop&rcm=ACoAAEcGAMgByNL8VRlNW9no7uklF_wVTugH2WU | https://www.linkedin.com/pulse/baby-boo-raises-11m-eur-enters-china-28-eu-markets-rgote/?trackingId=s8Y8zx7dSXSFuOfv0uxKLQ%3D%3D
Platform Trend Insights | Position YASO as an expert in the China space | “3 Douyin growth hacks beauty founders should know in 2025” | https://www.linkedin.com/posts/prisha-sekhsaria_beauty-brand-trips-2018-to-now-activity-7351487085821800448-Tgfd?utm_source=share&utm_medium=member_desktop&rcm=ACoAAEcGAMgByNL8VRlNW9no7uklF_wVTugH2WU | https://www.linkedin.com/posts/ludovicbacque_lancaekme-hellobike-china-activity-7351862342902554625-f5vB?utm_source=share&utm_medium=member_desktop&rcm=ACoAAEcGAMgByNL8VRlNW9no7uklF_wVTugH2WU | https://www.linkedin.com/posts/atiq31416_uxdesign-uxresearch-culturalux-activity-7350389523534499841-MoAb?utm_source=share&utm_medium=member_desktop&rcm=ACoAAEcGAMgByNL8VRlNW9no7uklF_wVTugH2WU | https://www.linkedin.com/posts/juniorborneli_startse-nowledge-agora-activity-7336799065617195010-XU6s?utm_source=share&utm_medium=member_desktop&rcm=ACoAAEcGAMgByNL8VRlNW9no7uklF_wVTugH2WU
Founder & Team Stories | Build trust and relatability | “Why we built YASO to keep brands in control — not controlled” | https://www.linkedin.com/posts/saahil-nayar-14b231a8_mila-beaute-raises-rs-18-crore-in-pre-series-activity-7311438921203077120--7HW?utm_source=share&utm_medium=member_desktop&rcm=ACoAAEcGAMgByNL8VRlNW9no7uklF_wVTugH2WU